## A
2017 LETTING SCHEDULE
AND DUE DATES
lett-sch.xlx | [5 empty] | 09/16/2016
ALL | PROJECTS | ADVERTISING | LETTING | COMMISSION | PLANS | PROPOSAL
DUE DATE TO | DEADLINE DATE TO | DATE | DATE | AWARD | PRINTING | PRINTING
CHECK SQUAD | C&E FOR PS&E |  |  | DATE
OCTOBER 30, 2016 | NOVEMBER 11, 2016 | DECEMBER 15, 2016 | JANUARY 12, 2017 (1) | JANUARY 19, 2017 | NOV. 29, 2016 | DEC. 06, 2016
NOVEMBER 27, 2016 | DECEMBER 09, 2016 | JANUARY 12, 2017 | FEBRUARY 09, 2017 (2) | FEBRUARY 16, 2017 | Dec. 27, 2016 | JAN. 03, 2017
DECEMBER 30, 2016 | JANUARY 13, 2017 | FEBRUARY 16, 2017 | MARCH 16, 2017 (3) | MARCH 23, 2017 | JAN. 31, 2017 | FEB. 07, 2017
JANUARY 27, 2017 | FEBRUARY 10, 2017 | MARCH 16, 2017 | APRIL 13, 2017 (4) | APRIL 20, 2017 | FEB. 28, 2017 | MAR. 07, 2017
FEBRUARY 24, 2017 | MARCH 10, 2017 | APRIL 13, 2017 | MAY 11, 2017 (5) | MAY 18, 2017 | MARCH 28, 2017 | APRIL 04, 2017
CANCELLED
|  | (cancelled) | (cancelled) | (CANCELLED)
APRIL 28, 2017 | MAY 12, 2017 | JUNE 15, 2017 | JULY 13, 2017 (07) | JULY 20,2017 | May 30, 2017 | JUNE 06, 2017
|  | (cancelled) | (cancelled) | (CANCELLED)
JUNE 23, 2017 | JULY 07, 2017 | AUGUST 10, 2017 | SEPTEMBER 07 2017 (09) | SEPTEMBER 14, 2017 | JULY 25, 2017 | AUG 01, 2017
JULY 28, 2017 | AUGUST 11, 2017 | SEPTEMBER 14, 2017 | OCTOBER 12, 2017 (10) | OCTOBER 19, 2017 | AUG.29, 2017 | SEPT. 05, 2017
AUGUST 25, 2017 | SEPTEMBER 08, 2017 | OCTOBER 12, 2017 | NOVEMBER 09, 2017 (11) | NOVEMBER 16, 2017 | SEPT. 26, 2017 | OCT. 03, 2017
SEPTEMBER 21, 2017 | OCTOBER 05, 2017 | NOVEMBER 08, 2017 | DECEMBER 06, 2017 (12) | DECEMBER 07, 2017 | OCT. 23, 2017 | OCT. 30, 2017
BID OPENING
(1) @ SHERIDAN HOLIDAY INN |  | (7) @ CASPER HILTON GARDEN INN
(2) @ CHEYENNE LITTLE AMERICA |  | (8) @ CANCELLED
(3) @LARAMIE HOLIDAY INN |  | (9) @ SHERIDAN HOLIDAY INN
(4) @CODY HOLIDAY INN |  | (10) @LARAMIE HILTON GARDEN INN
(5) @ CASPER RAMKOTA |  | (11) @ CHEYENNE LITTLE AMERICA
(6) @ CANCELLED |  | (12) @ CASPER RAMKOTA